## Planning
Research Plan Test, Analysis & Simulation Project
Week | Date | Session I | Date | To Do | Attendance | Session II | Date | To Do | Attendance
3.6 | 2020-03-16 | Discord Session | 18/03 09:00-13:00 | ERDA Assgnm. 4 Research Plan | Attendance!B4:B14 | Discord Session | 19/03 13:00-17:00 | Finish ERDA Assgnm. 4 Finish Data Extraction | Attendance!C4:C14
3.7 | 2020-03-23 | Discord Session | 25/03 09:00-13:00 | Start Data Analysis: Physical Model | Attendance!D4:D14 | Discord Session | 26/03 13:00-17:00 | Data Analysis: Physical Model Meeting Guido? | Attendance!E4:E14
3.8 | 2020-03-30 | Self work | 30/03-05/04 | Data Analysis: Finish Physical Model
3.9 | 2020-04-06 | Self work | 06/04-12/04 | Data Analysis: Implementation Kalman Filter
3.10 | 2020-04-13 | Self work | 13/04-19/04 | Data Analysis: Implementation Kalman Filter
4.1 | 2020-04-20 | Project/Discord Session | 21/03 13:45-17:30 | Data Analysis: Finish Kalman Filter implementation | Attendance!F4:F14
4.2 | 2020-04-27 | Project/Discord Session | 28/04 13:45-17:30 | Scientific Writing: Start Article (Draft) Data Analysis: Finish Analysis | Attendance!G4:G14 | Project/Discord | 30/04 13:45-17:30 | Scientific Writing: Article (Draft) Meeting Guido? | Attendance!H4:H14
4.3 | 2020-05-04 | Project/Discord Session | 07/05 13:45-17:30 | Scientific Writing: Article (Draft) Additional Exercise? Meeting Guido? | Attendance!I4:I14
4.4.1 | 2020-05-11 | Project/Discord Session | 12/05 13:45-17:30 | Scientific Writing: Article (Draft) Finish | Attendance!J4:J14
Deadline Draft Scientific Article | 2020-05-13
4.4.2 | 2020-05-14 | Home session | 15/05 08:45-12:30 | Scientifc Writing: Article (final) | Attendance!K4:K14
4.5 | 2020-05-18 | Home session | 20/05 13:45-17:30 | Scientifc Writing: Article (final) | Attendance!L4:L14
4.6 | 2020-05-25 | Home session | 25/05 13:45-17:00 | Scientifc Writing: Article (final) | Attendance!M4:M14 | Home session | 27/05 13:45-17:00 | Scientifc Writing: Article (final) | Attendance!N4:N14
4.7 | 2020-06-01 | Home session | 02/06 13:45-17:00 | Scientifc Writing: Article (final) | Attendance!O4:O14
4.8 | 2020-06-08 | Home session | 10/06 13:45-17:00 | Scientifc Writing: Article (final) | Attendance!P4:P14
Deadline Final Scientific Article | 2020-06-12
4.9-4.11 | 15/06/2020-22/06/2020 | Oral Exams

## Attendance
Attendance
Session | 18/03 09:00-13:00 | 19/03 13:00-17:00 | 25/03 09:00-13:00 | 26/03 13:00-17:00 | 21/03 13:45-17:30 | 28/04 13:45-17:30 | 30/04 13:45-17:30 | 07/05 13:45-17:30 | 12/05 13:45-17:30 | 15/05 08:45-12:30 | 20/05 13:45-17:30 | 25/05 13:45-17:00 | 27/05 13:45-17:00 | 02/06 13:45-17:00 | 10/06 13:45-17:00
Mateo
Winand
Jasper
Lars
Noah
Lars
Bavo
Seppe
Tristan
Pim
Legend
xxx xx-xx | Project Session
xxx xx-xx | Home session
Present
Unsure
Absent